## Sheet1
S.No | Date | Task Description | Spend time (Min) | Status | Comment
1 | 04/21/2023 | Environment setup | 15 | Facing Ioncube issue
2 | 04/22/2023 | Environment setup & issue discuss | 30 | Done
3 | 04/22/2023 | Category not found issue and checking my booking and cancel booking | 90 | Done
4 | 04/22/2023 | Remove my profie, change password, logout menu in my booking page and path update | 20 | Done
5 | 04/22/2023 | Painter list update and visitor contact form analysis | 20 | Done
6 | 04/23/2023 | Painter list update and visitor contact form update | 80 | Done
7 | 04/24/2023 | List evaluation complete status update functionality (mail with document) | 45 | In progress
8 | 04/29/2023 | List evaluation complete status update functionality (mail with document) | 30 | In progress
9 | 2023-05-01 | List evaluation complete status update functionality (mail with document) | 60 | Done
10 | 2023-05-02 | Auction view error update | 90 | Done
11 | 2023-05-04 | Property image view in view page | 40 | Done | Need to update the image width and size
12 | 2023-05-06 | Property image not saving properly | 110 | Done | Updated the agentcontroller saving logic
13 | 2023-05-11 | Property council data update to DB | 30 | Done
14 | 2023-05-25 | Property data Cakephp integration work | 50 | Done
15 | 2023-05-28 | Property api data integration demo | 30 | Done
16 | 2023-05-29 | API data integration work | 30 | Done
17 | 2023-05-30 | API data integration work | 80 | Done
18 | 2023-05-31 | API data integration work | 180 | Done
19 | 2023-06-01 | API data integration work | 90 | Done
20 | 2023-06-06 | Rent postform error fix | 70 | Done
21 | 2023-06-10 | Rent postform add more field error fix | 80 | Done
22 | 2023-06-11 | Private adevert post form error fix | 40 | Done
23 | 2023-06-18 | Map movement issue | 30 | Done
24 | 2023-06-26 | Map changing update | 20 | Done
25 | 2023-07-01 | Map errro and post date checking | 15 | Done
26 | 2023-07-03 | Previous date disable in public view property | 40 | Done